## Tickets
ID | Summary | Root Cause | Toolkit Version | Viewer Version | Issue Type | Defect Jira | Ticket Priority | Waiting Time | Investigation Effort | Assignee | Current Status | Ageing | Next Action Item | Comments | Date Created | Date Resolved | Linked Issues
DTVIEWER-19989 | Package Access Request for 652341 from MASE_UK |  |  | 724Access Ambulatory Viewer 1.3 | Issue Investigation |  | Medium | 0.0 days |  | Rucker, Shaun | Closed |  |  |  | 2025-12-02T02:47:49.000-0600 | 2025-12-02T11:42:41.000-0600
DTVIEWER-19988 | Connectivity issue after upgrading to 5.18 |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 7.0 days |  | Thakrar, Mihir | Waiting for Reporter Input |  |  |  | 2025-12-01T23:37:55.000-0600
DTVIEWER-19987 | RBA date is not synching after windows patch update |  |  | 724Access Downtime Viewer 5.15 | Issue Investigation |  | Medium | 7.0 days |  | Thakrar, Mihir | Waiting for Reporter Input |  |  |  | 2025-12-01T22:50:27.000-0600
DTVIEWER-19986 | Remote 724Access MySQL user account is not being rotated |  | 724Access Replication Management 2024.04.04 |  | Issue Investigation |  | Medium | 7.0 days |  | Thakrar, Mihir | Waiting for Reporter Input |  |  |  | 2025-12-01T19:33:22.000-0600
DTVIEWER-19984 | CGF_NY, DTV installation Error 'machinerowexists.jar'. |  |  | 724Access Downtime Viewer 5.13.1.1 | Issue Investigation |  | Medium | 3.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-12-01T14:54:21.000-0600 | 2025-12-05T06:54:21.000-0600
DTVIEWER-19983 | RFLUK72407 listener down |  | 724Access Replication Management 2022.03 |  | Issue Investigation |  | High | 7.0 days |  | Gaskell, Robin | Submitted |  |  |  | 2025-12-01T09:58:27.000-0600
DTVIEWER-19982 | Unable to see 724 node in olympus |  |  | 724Access Downtime Viewer 5.13.1.1 | Issue Investigation |  | Medium | 6.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-30T21:56:24.000-0600 | 2025-12-10T08:13:26.000-0600 | DTVIEWER-20033
DTVIEWER-19981 | Error while connecting to DTV during downtime. |  |  | 724Access Downtime Viewer 5.15 | Issue Investigation |  | Medium | 7.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-11-30T21:41:03.000-0600
DTVIEWER-19980 | HAMC_QAT: MySQL corruption due to improper device shutdowns. |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 8.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-11-28T12:23:44.000-0600
DTVIEWER-19979 | Resulted MRSA not pulling into Microbiology results on the viewer |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 8.0 days |  | Singhal, Avneesh | Investigation |  |  |  | 2025-11-28T09:33:18.000-0600
DTVIEWER-19977 | Errors creating credential store gg_credentialstore.py |  |  | 724Access Downtime Viewer 5.13.1 | Issue Investigation |  | Medium | 9.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-11-27T09:43:19.000-0600
DTVIEWER-19976 | WARNING: Unable to determine password for ... user |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 6.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-11-27T02:35:01.000-0600 | 2025-12-05T05:13:29.000-0600 | DTVIEWER-19685
DTVIEWER-19975 | Unable to successfully pull audits from the following devices |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 9.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-11-27T02:24:37.000-0600
DTVIEWER-19974 | 462483147 NRTH_GA needs CSN, Partial Log and trail file fixes applied |  |  | 724Access Downtime Viewer 5.16 | Issue Investigation |  | Medium | 10.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-11-26T14:57:30.000-0600
DTVIEWER-19973 | Package Access Request for 673494 from BAYC_FL |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 3.0 days |  | Rucker, Shaun | Closed |  |  |  | 2025-11-26T13:51:09.000-0600 | 2025-12-01T16:14:10.000-0600
DTVIEWER-19971 | CHSI_TN Unable to determine password for root user |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation |  | High | 3.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-11-26T10:57:07.000-0600 | 2025-12-01T23:21:43.000-0600
DTVIEWER-19969 | 462305991 CAMH_CD Remote upgrade not working to 5.17.1 on 2025.02.01 toolkit in PROD |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-26T08:48:48.000-0600 | 2025-12-08T15:27:38.000-0600
DTVIEWER-19965 | 462673434 LRMC_FL SSH Issues on 2025.01 and 5.17 |  | 724Access Replication Management 2025.01 |  | Issue Investigation |  | High | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-26T00:08:51.000-0600 | 2025-11-26T11:29:57.000-0600
DTVIEWER-19961 | SR 462641999 HUNT_AL Can't See 724 in Lights On. Olympus works fine. |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 11.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-25T08:22:01.000-0600
DTVIEWER-19960 | REGM_IA - Home Medications and Problem List in PROD does not match 724 |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation |  | Medium | 12.0 days |  | Bhansali, Pranjal | Waiting for Reporter Input |  |  |  | 2025-11-24T15:37:16.000-0600
DTVIEWER-19959 | TK 2025.04 sarail72403 mt_setup throws an error |  | 724Access Replication Management 2025.04 |  | Issue Investigation |  | Medium | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-24T11:48:21.000-0600 | 2025-11-24T14:56:17.000-0600
DTVIEWER-19958 | mt_setup script is not creating the required grants for role role_cern_724adm |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | Critical | 3.0 days |  | Datta, Saikat | Closed |  |  |  | 2025-11-24T06:38:02.000-0600 | 2025-11-28T06:33:26.000-0600
DTVIEWER-19957 | MDCH_AE: Vrep process abended with Incompatible record error |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-21T12:43:43.000-0600 | 2025-12-04T08:34:14.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19956 | MDCH_AE: Multiple vpumps are abended with Unexpected LOB record error |  | 724Access Replication Management 2024.02.OCI |  | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-21T12:38:20.000-0600 | 2025-12-04T08:34:37.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19955 | MHG_MS 462541668 Unable to open modify tab in Admin Tool |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 12.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-21T11:53:01.000-0600 | 2025-12-09T23:50:44.000-0600
DTVIEWER-19954 | TSSO_CD - Failing MT_SETUP FAILINIG at DB LINK test |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | High | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-21T10:42:42.000-0600 | 2025-11-21T14:33:44.000-0600 | DTVIEWER-19413
DTVIEWER-19950 | Related persons not displaying within 724 patient record |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 14.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-20T05:03:38.000-0600
DTVIEWER-19943 | 462388422 CHS_TN Need Assistance with 5.17 upgrade. SSH not functioning |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | High | 1.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-19T22:58:09.000-0600 | 2025-11-20T23:42:46.000-0600
DTVIEWER-19940 | GLAS_KY Pumper load error 'subprocess' is not defined. Did you forget to import 'subprocess'? |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation |  | Critical | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-19T10:33:12.000-0600 | 2025-11-20T09:47:42.000-0600
DTVIEWER-19938 | Local Admin Check Fails Due to Orphaned/Ghost Sids in Admin Group |  | 724Access Replication Management 2024.04.04 |  | Issue Investigation |  | Medium | 4.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-19T10:13:39.000-0600 | 2025-11-25T15:57:55.000-0600
DTVIEWER-19931 | GGSERR.LOG Filesize Correct Value |  | 724Access Replication Management 2024.04.04 |  | Issue Investigation |  | Medium | 5.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-18T16:36:57.000-0600 | 2025-11-26T06:06:44.000-0600 | DTVIEWER-18977, DTVIEWER-19966
DTVIEWER-19926 | Clarifications/concerns during non-prod testing (5.16.2) |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 16.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-18T02:33:07.000-0600 |  | DTVIEWER-20025
DTVIEWER-19918 | HAMC_QAT: Document Display |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 2.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-17T11:07:50.000-0600 | 2025-11-19T16:42:32.000-0600 | DTVIEWER-19942
DTVIEWER-19916 | u01 directory full on WSH724103 and MTPUMP on MT is abended. |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 17.0 days |  | Gaskell, Robin | Submitted |  |  |  | 2025-11-17T04:50:17.000-0600
DTVIEWER-19914 | Non-Expiring Document Tab in Global Prefs Search Bar Enhancement |  |  | 724Access Downtime Viewer - None | Issue Investigation |  | Medium | 1.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-14T10:26:05.000-0600 | 2025-11-17T13:50:57.000-0600 | DTVIEWER-19921
DTVIEWER-19912 | UNZA - intermittent SSH issues from Midtier to Workstation |  |  | 724Access Downtime Viewer 5.16.3 | Issue Investigation |  | Medium | 18.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-14T03:45:47.000-0600
DTVIEWER-19911 | Passwords not working post toolkit upgrade |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | Medium | 15.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-13T20:33:42.000-0600 | 2025-12-05T08:06:44.000-0600 | DTVIEWER-19985
DTVIEWER-19910 | SMRC_QAT: JSON return value is not valid error during the reverse ssh |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | Medium | 19.0 days |  | Bhansali, Pranjal | Waiting for Reporter Input |  |  |  | 2025-11-13T11:35:36.000-0600
DTVIEWER-19909 | DNAR Status not visible on DTV patient demographic banner unless you hover over it |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 7.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-13T09:18:44.000-0600 | 2025-11-24T13:38:16.000-0600
DTVIEWER-19907 | Patient list mismatch between Millennium and 724 DTV |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 5.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-13T03:40:32.000-0600 | 2025-11-20T10:43:16.000-0600
DTVIEWER-19906 | KING_AE: Multiple dtv load failures with Errors comparing table lists between parameter and report files |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | High | 17.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-13T00:49:44.000-0600 | 2025-12-08T05:48:53.000-0600
DTVIEWER-19905 | JDAM_GA -VPUMP Abended |  |  | 724Access Ambulatory Viewer 1.3.1 | Issue Investigation |  | Medium | 1.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-12T19:03:40.000-0600 | 2025-11-14T15:11:25.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19904 | ORHO_OK Allergy Reaction Information Not Crossing Over |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation |  | High | 20.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-12T16:05:14.000-0600
DTVIEWER-19901 | DUBO_PA - Requesting access for Package 656378 -5.15.2 724 DTV |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation |  | Medium | 0.0 days |  | Rucker, Shaun | Closed |  |  |  | 2025-11-12T11:46:44.000-0600 | 2025-11-12T14:42:10.000-0600
DTVIEWER-19899 | 462540091 CPTL_NH LOB, CSN, Trailfile fixes needed |  | 724Access Replication Management 2024.04.03 |  | Issue Investigation |  | Medium | 0.0 days |  | Gaskell, Robin | Closed |  |  |  | 2025-11-12T10:22:03.000-0600 | 2025-11-12T10:59:27.000-0600
DTVIEWER-19897 | KING_AE: Not able to install the DTV |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 17.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-12T06:10:01.000-0600 | 2025-12-08T05:47:35.000-0600
DTVIEWER-19892 | LCOX_MO - Issues installing Cygwin |  |  | 724Access Downtime Viewer 5.15 | Issue Investigation |  | Medium | 22.0 days |  | Bhansali, Pranjal | Waiting for Reporter Input |  |  |  | 2025-11-10T15:27:32.000-0600
DTVIEWER-19891 | CHR_NY Pre-Admit encounter on their Downtime Census, its not active encounter |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 22.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-10T14:19:38.000-0600
DTVIEWER-19890 | CDDN_UK 5.17/25.01 needs pc_find_next_rba and dtv clean up scrips fixed. |  |  | 724Access Downtime Viewer 5.17 | Issue Investigation |  | High | 1.0 days |  | Gaskell, Robin | Closed |  |  |  | 2025-11-10T10:30:50.000-0600 | 2025-11-11T10:40:47.000-0600
DTVIEWER-19889 | NBHS_CA, Data load Failure - VLOAD03 Fails due to Database error 1264. |  |  | 724Access Downtime Viewer - None | Issue Investigation |  | Medium | 22.0 days |  | Sun, Chloe | Waiting for Reporter Input |  |  |  | 2025-11-10T07:31:04.000-0600
DTVIEWER-19885 | HUNT_AL - mysql innodb corruption issue |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 20.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-07T18:06:01.000-0600 | 2025-12-08T05:07:21.000-0600
DTVIEWER-19883 | MT_SETUP Failure on Existing Midtier during Rebuild |  | 724Access Replication Management - None |  | Issue Investigation |  | Medium | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-07T16:25:42.000-0600 | 2025-11-07T17:05:07.000-0600 | DTVIEWER-19884
DTVIEWER-19882 | Need Assistance troubleshooting KMC_HI Admin tool |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 23.0 days |  | Thakrar, Mihir | Waiting for Reporter Input |  |  |  | 2025-11-07T12:31:58.000-0600
DTVIEWER-19881 | Enhancement to Improve visibility of unverified orders |  |  | 724Access Downtime Viewer 5.15.3 | Issue Investigation |  | Medium | 6.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-07T12:20:52.000-0600 | 2025-11-18T06:46:27.000-0600 | DTVIEWER-19927
DTVIEWER-19879 | FAIR_AK, Confusion regarding DTV password requirement. |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-07T07:03:33.000-0600 | 2025-11-07T08:50:34.000-0600 | DTVIEWER-18927
DTVIEWER-19878 | openSSH installation failing |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 7.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-07T06:13:26.000-0600 | 2025-11-18T08:14:46.000-0600
DTVIEWER-19875 | VGR - Unable to SSH from Source to MT |  |  | 724Access Downtime Viewer 5.18.1 | Issue Investigation |  | Medium | 17.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-06T14:29:55.000-0600 | 2025-12-01T23:50:58.000-0600
DTVIEWER-19874 | DTV load Failing |  |  | 724Access Downtime Viewer - None | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-06T11:02:35.000-0600 | 2025-11-19T10:20:00.000-0600
DTVIEWER-19872 | CCH_CD Apply fixes to environment |  | 724Access Replication Management - None |  | Issue Investigation |  | Medium | 7.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-06T09:57:35.000-0600 | 2025-11-17T15:34:51.000-0600 | DTVIEWER-19887
DTVIEWER-19871 | SR 462341708 LCAH_NCR DTV install failing to connect to database |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation |  | Medium | 11.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-06T08:42:51.000-0600 | 2025-11-21T14:31:33.000-0600
DTVIEWER-19870 | USC_CA Admin Tool and DTV Load Issues |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 1.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-06T08:15:31.000-0600 | 2025-11-07T13:07:59.000-0600
DTVIEWER-19869 | NAH_AZ: Admin Tool Installation Issues |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 0.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-06T08:05:59.000-0600 | 2025-11-06T08:09:10.000-0600
DTVIEWER-19865 | VLOAD01 Fails Due to CE_DYNAMIC_LABEL_ID Incorrect Value |  | 724Access Replication Management 2025.04 |  | Issue Investigation |  | Medium | 4.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-11-05T16:10:05.000-0600 | 2025-11-12T12:44:18.000-0600
DTVIEWER-19864 | 462641030 KTCH_CD Package Access Request 667795 |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | Medium | 25.0 days |  | Patel, Sameena | Waiting for Reporter Input |  |  |  | 2025-11-05T14:52:41.000-0600
DTVIEWER-19862 | CERN_COMC MidTier Alerting Emails |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 14.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-05T12:16:52.000-0600 | 2025-11-26T08:17:24.000-0600 | DTVIEWER-19529, DTVIEWER-19920, DTVIEWER-19880
DTVIEWER-19861 | LEWIS_UK - 724 DTV Printing Preference Issue (Build: 2022.03) |  | 724Access Replication Management 2024.04.03 |  | Issue Investigation |  | Medium | 5.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-05T11:58:21.000-0600 | 2025-11-13T03:36:25.000-0600
DTVIEWER-19860 | DEPH_MA full OCI setup, TK 2024.02.01.OCI BE_SETUP.ksh throwing an error |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 11.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-05T11:36:18.000-0600 | 2025-11-20T23:40:27.000-0600
DTVIEWER-19852 | Package Access Request for 673494 from AZSL_BE |  |  | 724Access Downtime Viewer 5.16.3 | Issue Investigation |  | Medium | 25.0 days |  | Gummala, Sruthi Reddy | Waiting for Reporter Input |  |  |  | 2025-11-05T01:49:43.000-0600
DTVIEWER-19848 | Monitoring not being pushed at end of mt_upgrade.ksh |  | 724Access Replication Management 2025.02 |  | Issue Investigation |  | Medium | 14.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-04T11:55:51.000-0600 | 2025-11-25T10:23:12.000-0600 | DTVIEWER-19839
DTVIEWER-19847 | ADVN_MD Monitoring tables need purge |  | 724Access Replication Management - None |  | Issue Investigation |  | Medium | 0.0 days |  | Gaskell, Robin | Closed |  |  |  | 2025-11-04T10:33:53.000-0600 | 2025-11-04T12:51:27.000-0600
DTVIEWER-19846 | Inquiry Regarding Future Date Limitations in MAR Printing via 724 Access Viewer |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 1.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-04T09:01:37.000-0600 | 2025-11-05T14:37:23.000-0600
DTVIEWER-19844 | Removing SITHS card from 724DTV does not logout user |  |  | 724Access Downtime Viewer 5.16.3 | Issue Investigation |  | Medium | 3.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-03T09:51:33.000-0600 | 2025-11-07T05:13:05.000-0600 | DTVIEWER-19876
DTVIEWER-19839 | MCLA_MI monitoring jar push due to lots of ssh alerts |  | 724Access Replication Management 2025.01.01 |  | Issue Investigation |  | Medium | 2.0 days |  | Gaskell, Robin | Closed |  |  |  | 2025-11-03T04:38:02.000-0600 | 2025-11-05T12:10:16.000-0600 | DTVIEWER-18301, DTVIEWER-19848
DTVIEWER-19834 | 462466828 CCH_CD Package Access Request for 650541 |  |  | 724Access Downtime Viewer 5.15.1 | Issue Investigation |  | Medium | 1.0 days |  | Rucker, Shaun | Closed |  |  |  | 2025-10-31T08:46:01.000-0500 | 2025-11-03T09:24:26.000-0600
DTVIEWER-19833 | Olympus monitoring not working for device |  | 724Access Replication Management 2025.02.02 |  | Issue Investigation |  | Medium | 3.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-10-31T06:33:30.000-0500 | 2025-11-05T07:57:24.000-0600
DTVIEWER-19832 | Issue with openSSH install during 5.16.2 DTV installation |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 12.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-10-31T02:48:21.000-0500 | 2025-11-18T08:13:13.000-0600
DTVIEWER-19828 | MASE_UK - Package Access Request for 665947 |  |  | 724Access Downtime Viewer 5.18.1 | Issue Investigation |  | Medium | 4.0 days |  | Rucker, Shaun | Closed |  |  |  | 2025-10-30T13:33:27.000-0500 | 2025-11-05T15:17:36.000-0600 | DTVIEWER-19565
DTVIEWER-19821 | Backend setup fails with asking to run Run /atg/dr/724dtv/v5.4/sql/create_user_OCI.sql as SYSDBA |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | Medium | 9.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-10-30T12:04:23.000-0500 | 2025-11-12T14:04:35.000-0600
DTVIEWER-19817 | SMRC_QA: Insecure File Permission on ggs |  |  | 724Access Downtime Viewer 5.15 | Issue Investigation |  | Medium | 5.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-10-30T05:18:09.000-0500 | 2025-11-06T07:58:03.000-0600 | DTVIEWER-19424
DTVIEWER-19814 | EAST_ME NED Inconsistency on all devices post NEDLOAD |  |  | 724Access Ambulatory Viewer 1.4 | Issue Investigation |  | Medium | 18.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-10-29T10:59:22.000-0500 | 2025-11-25T03:21:19.000-0600 | DTVIEWER-19929, DTVIEWER-19465
DTVIEWER-19803 | VM Firewall Delay Causing IAM Timeout |  |  | 724Access Downtime Viewer 5.18.OCI | Issue Investigation |  | Medium | 10.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-10-28T13:40:36.000-0500 | 2025-11-12T11:17:55.000-0600 | DTVIEWER-19802
DTVIEWER-19802 | VM Firewall Delay Causing IAM Timeout |  |  | 724Access Downtime Viewer 5.18.OCI | Issue Investigation |  | Medium | 5.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-10-28T13:37:20.000-0500 | 2025-11-05T09:08:12.000-0600 | DTVIEWER-19803
DTVIEWER-19801 | Token Not Generated When Logging in Immediately After Closing Application |  |  | 724Access Downtime Viewer 5.18.OCI | Issue Investigation | DTVIEWER-19900 | Medium | 10.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-10-28T13:33:54.000-0500 | 2025-11-12T11:14:48.000-0600
DTVIEWER-19796 | unable to remove patients with Length of Stay (LOS) > 48hrs in DTV ED Tracking board |  |  | 724Access Downtime Viewer 5.15.1 | Issue Investigation |  | Medium | 19.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-28T00:33:57.000-0500 | 2025-11-24T02:16:11.000-0600
DTVIEWER-19793 | mt_upgrade/mt_setup doesn't enable stats job |  | 724Access Replication Management 2025.02.02 |  | Issue Investigation |  | Medium | 7.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-10-27T04:41:25.000-0500 | 2025-11-05T12:22:57.000-0600 | DTVIEWER-19863
DTVIEWER-19787 | Purge script running well into the next day |  |  | 724Access Downtime Viewer 5.16.1 | Issue Investigation |  | Medium | 19.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-10-24T09:35:03.000-0500 | 2025-11-21T07:57:58.000-0600 | DTVIEWER-19749
DTVIEWER-19782 | DTV is not loading after upgrading to 5.18 |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 17.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-23T22:04:04.000-0500 | 2025-11-18T02:59:33.000-0600 | DTVIEWER-19830
DTVIEWER-19781 | 724Access Install Issues (USAL_AL) |  |  | 724Access Ambulatory Viewer 1.3 | Issue Investigation |  | Medium | 14.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-23T17:10:48.000-0500 | 2025-11-12T23:51:14.000-0600
DTVIEWER-19778 | CCH_CD: Client is requesting help with installing OCI Admin Tool |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | High | 27.0 days |  | Thakrar, Mihir | Closed |  |  |  | 2025-10-23T12:57:39.000-0500 | 2025-12-02T09:14:24.000-0600 | DTVIEWER-19772
DTVIEWER-19773 | QEMR_AU: Intake and Output volume is not matching with the Millennium. |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 12.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-23T11:19:50.000-0500 | 2025-11-11T06:57:50.000-0600
DTVIEWER-19763 | 5.18 upgrader failing with Unable to copy secure definitions |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | High | 14.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-21T15:26:09.000-0500 | 2025-11-11T03:29:12.000-0600
DTVIEWER-19740 | CAMH_CD Remote upgrade not working to 5.17.1 on 2025.02.01 toolkitin PROD |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | High | 19.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-16T16:16:12.000-0500 | 2025-11-13T00:52:24.000-0600
DTVIEWER-19702 | HS_AL: Update OSHI/JNA version in 724monitoring.jar |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 19.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-14T11:39:19.000-0500 | 2025-11-10T23:38:26.000-0600 | DTVIEWER-18912, DTVIEWER-19794
DTVIEWER-19685 | WARNING: Unable to determine password for ... user |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 23.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-10-10T08:26:39.000-0500 | 2025-11-12T09:32:41.000-0600 | DTVIEWER-19976
DTVIEWER-19603 | RESK_SE - 724: Search patient tab, column Other doesn't display å ä ö |  |  | 724Access Downtime Viewer 5.16.3 | Issue Investigation |  | Low | 31.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-09-25T04:04:28.000-0500 | 2025-11-07T06:27:01.000-0600 | DTVIEWER-16475, DTVIEWER-19791
DTVIEWER-19601 | MUNS_MI, Unable to Collect Audit Logs via 724Access Admin Tool |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 38.0 days |  | Dhingra, Gaurav | Closed |  |  |  | 2025-09-24T12:25:24.000-0500 | 2025-11-18T03:01:18.000-0600
DTVIEWER-19529 | SHCN_AU ¦¦ Non-Prod ¦¦ Reverse ssh is not working |  |  | 724Access Downtime Viewer 5.15.1 | Issue Investigation |  | Low | 47.0 days |  | Datta, Saikat | Closed |  |  |  | 2025-09-11T01:50:13.000-0500 | 2025-11-17T02:31:00.000-0600 | DTVIEWER-19862
DTVIEWER-19293 | remove all ordered Blood work in ccd report Within the 724 Ambulatory Viewer |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 69.0 days |  | Singla, Rahul | Closed |  |  |  | 2025-08-11T13:58:21.000-0500 | 2025-11-17T12:04:12.000-0600 | DTVIEWER-19313
DTVIEWER-19217 | KMC_HI-724 DTV OCI Redeployment Cleanup |  | 724Access Replication Management - None |  | Issue Investigation |  | Medium | 78.0 days |  | Botta, Venkata Satya Prasanth Kumar | Closed |  |  |  | 2025-07-30T12:16:56.000-0500 | 2025-11-18T11:14:33.000-0600 | DTVIEWER-19930
DTVIEWER-19178 | OUH_UK Anesthetic Chart View shows one page when there are multiples |  |  | 724Access Downtime Viewer 5.15.1 | Issue Investigation |  | Medium | 74.0 days |  | Adhikari, Tamal | Closed |  |  |  | 2025-07-23T14:52:41.000-0500 | 2025-11-04T21:43:54.000-0600
DTVIEWER-19176 | Certain items in lab results and patient care results appear multiple times in patient records in 724AccessViewer. |  |  | 724Access Downtime Viewer 5.16.1 | Issue Investigation |  | Medium | 76.0 days |  | Adhikari, Tamal | Closed |  |  |  | 2025-07-23T09:23:31.000-0500 | 2025-11-07T07:24:58.000-0600
DTVIEWER-19043 | Cannot create view AMB 1.4 |  |  | 724Access Ambulatory Viewer 1.3 | Issue Investigation |  | High | 103.0 days |  | Adhikari, Tamal | Closed |  |  |  | 2025-06-25T05:14:15.000-0500 | 2025-11-18T00:18:09.000-0600 | DTVIEWER-18061
DTVIEWER-19040 | BHS_FL Requested for SvcD7A Password to be Encrypted during install of 5.15+ DTV |  |  | 724Access Downtime Viewer 5.15.2 | Issue Investigation | DTVIEWER-19902 | Medium | 101.0 days |  | Bolls, Aeja | Closed |  |  |  | 2025-06-24T11:00:15.000-0500 | 2025-11-12T11:55:15.000-0600
DTVIEWER-18954 | HAMC_QAT: Windows version not reflecting correctly in Olympus |  |  | 724Access Downtime Viewer 5.16.2 | Issue Investigation |  | Medium | 115.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-05-29T06:56:14.000-0500 | 2025-11-06T12:35:32.000-0600 | DTVIEWER-19753
DTVIEWER-20021 | Package Access Request for 667795 from JAMES_IE |  | 724Access Replication Management 2025.01 |  | Issue Investigation |  | Medium | 0.0 days |  | Rucker, Shaun | Closed |  |  |  | 2025-12-09T02:52:02.000-0600 | 2025-12-09T15:25:56.000-0600
DTVIEWER-20020 | LHSC_CD - Some Documents Not Populating in 724 Ambulatory |  |  | 724Access Ambulatory Viewer 1.3.0.1 | Issue Investigation |  | Medium | 2.0 days |  | Singhal, Avneesh | Investigation |  |  |  | 2025-12-08T16:53:07.000-0600
DTVIEWER-20016 | USC_CA Load error C++ mismatch |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 3.0 days |  | Thakrar, Mihir | Submitted |  |  |  | 2025-12-05T10:50:09.000-0600
DTVIEWER-20015 | SR 462994430 LCAH_NCR Data load failing due to MySQL unzip failing |  | 724Access Replication Management 2024.04.04 |  | Issue Investigation |  | Medium | 3.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-12-05T09:51:21.000-0600
DTVIEWER-20012 | If a patient has No Known Medication Allergies and No Known Allergies documented within the Allergies component within an MPage, then the 724 inpatient drug chart only displays No Known Medication Allergies |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 3.0 days |  | Singhal, Avneesh | Waiting for Reporter Input |  |  |  | 2025-12-05T01:57:55.000-0600
DTVIEWER-20009 | KING_AE: Load failure - Could not translate host name KCHMAMC724D01 into an Internet address |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 1.0 days |  | Datta, Saikat | Closed |  |  |  | 2025-12-04T23:10:58.000-0600 | 2025-12-08T06:07:43.000-0600
DTVIEWER-19984 | CGF_NY, DTV installation Error 'machinerowexists.jar'. |  |  | 724Access Downtime Viewer 5.13.1.1 | Issue Investigation |  | Medium | 3.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-12-01T14:54:21.000-0600 | 2025-12-05T06:54:21.000-0600
DTVIEWER-19976 | WARNING: Unable to determine password for ... user |  | 724Access Replication Management 2024.04.02.01 |  | Issue Investigation |  | Medium | 6.0 days |  | Singhal, Avneesh | Closed |  |  |  | 2025-11-27T02:35:01.000-0600 | 2025-12-05T05:13:29.000-0600 | DTVIEWER-19685
DTVIEWER-19969 | 462305991 CAMH_CD Remote upgrade not working to 5.17.1 on 2025.02.01 toolkit in PROD |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-26T08:48:48.000-0600 | 2025-12-08T15:27:38.000-0600
DTVIEWER-19957 | MDCH_AE: Vrep process abended with Incompatible record error |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-21T12:43:43.000-0600 | 2025-12-04T08:34:14.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19956 | MDCH_AE: Multiple vpumps are abended with Unexpected LOB record error |  | 724Access Replication Management 2024.02.OCI |  | Issue Investigation |  | Medium | 8.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-21T12:38:20.000-0600 | 2025-12-04T08:34:37.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19955 | MHG_MS 462541668 Unable to open modify tab in Admin Tool |  |  | 724Access Downtime Viewer 5.17.1 | Issue Investigation |  | Medium | 12.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-21T11:53:01.000-0600 | 2025-12-09T23:50:44.000-0600
DTVIEWER-19911 | Passwords not working post toolkit upgrade |  |  | 724Access Replication Managemen 2025.02.01 | Issue Investigation |  | Medium | 15.0 days |  | Sun, Chloe | Closed |  |  |  | 2025-11-13T20:33:42.000-0600 | 2025-12-05T08:06:44.000-0600 | DTVIEWER-19985
DTVIEWER-19906 | KING_AE: Multiple dtv load failures with Errors comparing table lists between parameter and report files |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | High | 17.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-13T00:49:44.000-0600 | 2025-12-08T05:48:53.000-0600
DTVIEWER-19897 | KING_AE: Not able to install the DTV |  |  | 724Access Downtime Viewer 5.15.OCI | Issue Investigation |  | Medium | 17.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-12T06:10:01.000-0600 | 2025-12-08T05:47:35.000-0600
DTVIEWER-19885 | HUNT_AL - mysql innodb corruption issue |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 20.0 days |  | Bhansali, Pranjal | Closed |  |  |  | 2025-11-07T18:06:01.000-0600 | 2025-12-08T05:07:21.000-0600
DTVIEWER-19804 | CHH_WV 724Access DTV Install Error |  |  | 724Access Downtime Viewer 5.18 | Issue Investigation |  | Medium | 28.0 days |  | Thakrar, Mihir | Closed |  |  |  | 2025-10-28T14:46:59.000-0500 | 2025-12-08T11:35:18.000-0600