## Tickets
ID | Summary | Root Cause | Toolkit Version | Viewer Version | Issue Type | Defect Jira | Ticket Priority | Waiting Time | Investigation Effort | Assignee | Current Status | Ageing | Next Action Item | Comments | Date Created | Date Resolved | Linked Issues
DTVIEWER-20020 | LHSC_CD - Some Documents Not Populating in 724 Ambulatory | null | N/A | 724Access Ambulatory Viewer 1.3.0.1 | Issue Investigation | No Defect Jira | Medium | 2.0 days | null | Singhal, Avneesh | Investigation | null | null | null | 2025-12-08T16:53:07.000-0600
DTVIEWER-20017 | Display location selected in locations view | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null |  | Open | null | null | null | 2025-12-08T10:28:16.000-0600
DTVIEWER-20016 | USC_CA Load error C++ mismatch | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | No Defect Jira | Medium | 3.0 days | null | Thakrar, Mihir | Submitted | null | null | null | 2025-12-05T10:50:09.000-0600
DTVIEWER-20015 | SR 462994430 LCAH_NCR Data load failing due to MySQL unzip failing | null | 724Access Replication Management 2024.04.04 | N/A | Issue Investigation | No Defect Jira | Medium | 3.0 days | null | Singhal, Avneesh | Waiting for Reporter Input | null | null | null | 2025-12-05T09:51:21.000-0600
DTVIEWER-20014 | Unable to run 724auth-filter-config.jar | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Costa, Floid | In Review | null | null | null | 2025-12-05T04:20:31.000-0600
DTVIEWER-20013 | Unable to run admin_monitor.ksh ggstatshourly | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-12-05T04:17:52.000-0600 | 2025-12-09T12:23:37.000-0600
DTVIEWER-20012 | If a patient has No Known Medication Allergies and No Known Allergies documented within the Allergies component within an MPage, then the 724 inpatient drug chart only displays No Known Medication Allergies | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | No Defect Jira | Medium | 3.0 days | null | Singhal, Avneesh | Waiting for Reporter Input | null | null | null | 2025-12-05T01:57:55.000-0600
DTVIEWER-20009 | KING_AE: Load failure - Could not translate host name KCHMAMC724D01 into an Internet address | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | No Defect Jira | Medium | 1.0 days | null | Datta, Saikat | Closed | null | null | null | 2025-12-04T23:10:58.000-0600 | 2025-12-08T06:07:43.000-0600
DTVIEWER-19998 | Encntr_Domain value not getting replicated to Mid from Source | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Saha, Sudipta | Issue Done | null | null | null | 2025-12-04T06:13:13.000-0600 | 2025-12-04T22:51:57.000-0600
DTVIEWER-19996 | DTVs are failing to update | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | No Defect Jira | Medium | 5.0 days | null | Thakrar, Mihir | Waiting for Reporter Input | null | null | null | 2025-12-03T12:28:05.000-0600
DTVIEWER-19995 | TK 2025.02.03 - PC Load getting failed with JRE not found error | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Saha, Sudipta | Closed | null | null | null | 2025-12-03T10:16:42.000-0600 | 2025-12-04T10:21:08.000-0600
DTVIEWER-19994 | Same encounter has multiple MRN associated with it. | null | 724Access Replication Management 2024.04 | N/A | Issue Investigation | No Defect Jira | Medium | 5.0 days | null | Singhal, Avneesh | Investigation | null | null | null | 2025-12-03T08:13:21.000-0600
DTVIEWER-19993 | Rest setup is not complete either maybe cert issue or/& authbind on OEL8. | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Costa, Floid | Open | null | null | null | 2025-12-03T02:49:20.000-0600
DTVIEWER-19992 | MT_UPGRADE is failing with latest 2025.02.03 code change after taking JRE changes | null | N/A | N/A | Sub-task | No Defect Jira | Critical |  | null | Saha, Sudipta | Issue Done | null | null | null | 2025-12-03T00:44:40.000-0600 | 2025-12-03T02:43:32.000-0600
DTVIEWER-19991 | BE_UPGRADE is failing with latest 2025.02.03 code change after taking JRE changes | null | N/A | N/A | Sub-task | No Defect Jira | Critical |  | null | Saha, Sudipta | Closed | null | null | null | 2025-12-03T00:09:09.000-0600 | 2025-12-03T00:21:47.000-0600
DTVIEWER-19989 | Package Access Request for 652341 from MASE_UK | null | N/A | 724Access Ambulatory Viewer 1.3 | Issue Investigation | No Defect Jira | Medium | 0.0 days | null | Rucker, Shaun | Closed | null | null | null | 2025-12-02T02:47:49.000-0600 | 2025-12-02T11:42:41.000-0600
DTVIEWER-19988 | Connectivity issue after upgrading to 5.18 | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | No Defect Jira | Medium | 7.0 days | null | Thakrar, Mihir | Waiting for Reporter Input | null | null | null | 2025-12-01T23:37:55.000-0600
DTVIEWER-19987 | RBA date is not synching after windows patch update | null | N/A | 724Access Downtime Viewer 5.15 | Issue Investigation | No Defect Jira | Medium | 7.0 days | null | Thakrar, Mihir | Waiting for Reporter Input | null | null | null | 2025-12-01T22:50:27.000-0600
DTVIEWER-19986 | Remote 724Access MySQL user account is not being rotated | null | 724Access Replication Management 2024.04.04 | N/A | Issue Investigation | No Defect Jira | Medium | 7.0 days | null | Thakrar, Mihir | Waiting for Reporter Input | null | null | null | 2025-12-01T19:33:22.000-0600
DTVIEWER-19984 | CGF_NY, DTV installation Error 'machinerowexists.jar'. | null | N/A | 724Access Downtime Viewer 5.13.1.1 | Issue Investigation | No Defect Jira | Medium | 3.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-12-01T14:54:21.000-0600 | 2025-12-05T06:54:21.000-0600
DTVIEWER-19983 | RFLUK72407 listener down | null | 724Access Replication Management 2022.03 | N/A | Issue Investigation | No Defect Jira | High | 7.0 days | null | Gaskell, Robin | Submitted | null | null | null | 2025-12-01T09:58:27.000-0600
DTVIEWER-19976 | WARNING: Unable to determine password for ... user | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | No Defect Jira | Medium | 6.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-27T02:35:01.000-0600 | 2025-12-05T05:13:29.000-0600 | DTVIEWER-19685
DTVIEWER-19973 | Package Access Request for 673494 from BAYC_FL | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | No Defect Jira | Medium | 3.0 days | null | Rucker, Shaun | Closed | null | null | null | 2025-11-26T13:51:09.000-0600 | 2025-12-01T16:14:10.000-0600
DTVIEWER-19971 | CHSI_TN Unable to determine password for root user | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | No Defect Jira | High | 3.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-26T10:57:07.000-0600 | 2025-12-01T23:21:43.000-0600
DTVIEWER-19969 | 462305991 CAMH_CD Remote upgrade not working to 5.17.1 on 2025.02.01 toolkit in PROD | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | No Defect Jira | Medium | 8.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-26T08:48:48.000-0600 | 2025-12-08T15:27:38.000-0600
DTVIEWER-19957 | MDCH_AE: Vrep process abended with Incompatible record error | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | No Defect Jira | Medium | 8.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-21T12:43:43.000-0600 | 2025-12-04T08:34:14.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19956 | MDCH_AE: Multiple vpumps are abended with Unexpected LOB record error | null | 724Access Replication Management 2024.02.OCI | N/A | Issue Investigation | No Defect Jira | Medium | 8.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-21T12:38:20.000-0600 | 2025-12-04T08:34:37.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19911 | Passwords not working post toolkit upgrade | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | No Defect Jira | Medium | 15.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-13T20:33:42.000-0600 | 2025-12-05T08:06:44.000-0600 | DTVIEWER-19985
DTVIEWER-19906 | KING_AE: Multiple dtv load failures with Errors comparing table lists between parameter and report files | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | No Defect Jira | High | 17.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-13T00:49:44.000-0600 | 2025-12-08T05:48:53.000-0600
DTVIEWER-19897 | KING_AE: Not able to install the DTV | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | No Defect Jira | Medium | 17.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-12T06:10:01.000-0600 | 2025-12-08T05:47:35.000-0600
DTVIEWER-19885 | HUNT_AL - mysql innodb corruption issue | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | No Defect Jira | Medium | 20.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-07T18:06:01.000-0600 | 2025-12-08T05:07:21.000-0600
DTVIEWER-19875 | VGR - Unable to SSH from Source to MT | null | N/A | 724Access Downtime Viewer 5.18.1 | Issue Investigation | No Defect Jira | Medium | 17.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-06T14:29:55.000-0600 | 2025-12-01T23:50:58.000-0600
DTVIEWER-19804 | CHH_WV 724Access DTV Install Error | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | No Defect Jira | Medium | 28.0 days | null | Thakrar, Mihir | Closed | null | null | null | 2025-10-28T14:46:59.000-0500 | 2025-12-08T11:35:18.000-0600
DTVIEWER-19778 | CCH_CD: Client is requesting help with installing OCI Admin Tool | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | No Defect Jira | High | 27.0 days | null | Thakrar, Mihir | Closed | null | null | null | 2025-10-23T12:57:39.000-0500 | 2025-12-02T09:14:24.000-0600 | DTVIEWER-19772
DTVIEWER-19573 | CHWB_CA want to disable MD5 via Nartac and need to know if it will affect 724 | null | 724Access Replication Management 2025.01.01 | N/A | Issue Investigation | No Defect Jira | Medium | 54.0 days | null | Patel, Sameena | Closed | null | null | null | 2025-09-17T14:13:28.000-0500 | 2025-12-03T12:53:17.000-0600
DTVIEWER-19565 | Package Access Request for 665947 from MASE_UK | null | N/A | 724Access Downtime Viewer 5.18.1 | Issue Investigation | No Defect Jira | Medium | 55.0 days | null | Patel, Sameena | Closed | null | null | null | 2025-09-17T03:18:20.000-0500 | 2025-12-03T12:52:35.000-0600 | DTVIEWER-19828
DTVIEWER-19442 | QEMR_AU: Upgrade plan | null | 724Access Replication Management 2025.01.01 | N/A | Issue Investigation | No Defect Jira | Medium | 67.0 days | null | Patel, Sameena | Closed | null | null | null | 2025-09-01T07:51:33.000-0500 | 2025-12-03T13:42:25.000-0600
DTVIEWER-19255 | Enable Admin Tool LDAP Login Workflow - Non-OCI | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-08-05T09:10:44.000-0500 | 2025-12-08T13:28:01.000-0600
DTVIEWER-19254 | LDAP Login Workflow - OCI | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-08-05T09:09:48.000-0500 | 2025-12-08T13:27:37.000-0600
DTVIEWER-19219 | JDAM_GA - Requesting general guidance to update DTV from related flash FLASH25-0142-0 | null | N/A | 724Access Downtime Viewer 5.15 | Issue Investigation | No Defect Jira | Medium | 89.0 days | null | Patel, Sameena | Closed | null | null | null | 2025-07-30T14:10:30.000-0500 | 2025-12-03T13:40:44.000-0600
DTVIEWER-18811 | Onboarding flow | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-23T11:44:16.000-0500 | 2025-12-08T13:27:24.000-0600
DTVIEWER-18808 | Jet UI Unit Testing - Phase 2 | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-22T17:09:45.000-0500 | 2025-12-08T13:26:52.000-0600
DTVIEWER-18807 | Jet UI Unit Testing - Phase 1 | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-22T17:08:52.000-0500 | 2025-12-08T13:26:44.000-0600 | DTVIEWER-18794
DTVIEWER-18786 | UI Design and Accessibility | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-21T12:07:11.000-0500 | 2025-12-08T13:26:34.000-0600
DTVIEWER-18781 | Device Menu | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-21T11:33:46.000-0500 | 2025-12-08T13:26:25.000-0600
DTVIEWER-18780 | Global Menu Dropdown | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-21T11:33:29.000-0500 | 2025-12-08T13:26:22.000-0600
DTVIEWER-18779 | Global Preferences - Security View | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-21T11:32:39.000-0500 | 2025-12-08T13:26:18.000-0600
DTVIEWER-18778 | Downtime Data Maintenance View | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-04-21T11:32:14.000-0500 | 2025-12-08T13:26:14.000-0600
DTVIEWER-18474 | Jenkin pipeline setup | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Nimbalkar, Poonam | Closed | null | null | null | 2025-02-24T16:05:14.000-0600 | 2025-12-08T18:27:09.000-0600
DTVIEWER-18472 | DB script file creation | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2025-02-24T16:02:35.000-0600 | 2025-12-08T13:11:20.000-0600
DTVIEWER-18230 | 724Access Enhancement Request - Automate DTV Upgrade without admin tool | null | N/A | 724Access Downtime Viewer 5.15 | Issue Investigation | No Defect Jira | Medium | 250.0 days | null | Patel, Sameena | Closed | null | null | null | 2024-12-18T11:48:27.000-0600 | 2025-12-03T13:47:27.000-0600 | DTVIEWER-19997
DTVIEWER-18190 | Deployment and packaging along with rest service | null | N/A | N/A | Sub-task | No Defect Jira | Medium |  | null | Sun, Chloe | Closed | null | null | null | 2024-12-05T16:49:55.000-0600 | 2025-12-08T13:52:22.000-0600